## Cover
PulseDesk — Project Timeline
Document ID | PD-TL-001
Version | 1.0
Date | 2026-08-01
Prepared by | TandSol
Status | Living
Related documents | PD-PMP-001, PD-CHR-001
Classification | Internal
Revision note | v1.0 — initial baseline issued with the first working build.

## Timeline
Phase | Name | Activities | Start | End | Duration | Owner | Parallel/Sequential
Phase 1 | Discovery | Scope the seven requested panels, choose free keyless data sources, verify each endpoint responds | 2026-08-01 | 2026-08-01 | 1 day | Owner | Sequential
Phase 2 | Architecture | Main/renderer split, IPC surface, tiered refresh design, storage layout | 2026-08-01 | 2026-08-01 | 1 day | Owner | Sequential
Phase 3 | Data services | stocks, news, sentiment, crypto, weather, portfolio, market, http, icon | 2026-08-01 | 2026-08-01 | 1 day | Owner | Parallel
Phase 4 | Shell | Frameless pinned window, tray menu, global shortcuts, settings persistence | 2026-08-01 | 2026-08-01 | 1 day | Owner | Parallel
Phase 5 | Interface | Vibrant glass theme, card grid, SVG sparklines and donut, modals, compact mode | 2026-08-01 | 2026-08-01 | 1 day | Owner | Sequential
Phase 6 | Verification | Live smoke test of all services, layout audit at three widths, security review | 2026-08-01 | 2026-08-01 | 1 day | Owner | Sequential
Phase 7 | Documentation | Handbook plus the nine controlled documents | 2026-08-01 | 2026-08-01 | 1 day | Owner | Sequential
Phase 8 | Roadmap | Broker CSV import, sell flow, alerts, corporate actions, signed installer | 2026-08-04 | 2026-10-31 | 13 weeks | Owner | Sequential

## Gantt
Phase | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14
Phase 1 Discovery
Phase 2 Architecture
Phase 3 Data services
Phase 4 Shell
Phase 5 Interface
Phase 6 Verification
Phase 7 Documentation
Phase 8 Roadmap

## Summary
Metric | Value
Phases
Parallel phases
Sequential phases
Build completed on
Roadmap ends