## Cover
PulseDesk — Risk Register
Document ID | PD-RSK-001
Version | 1.0
Date | 2026-08-01
Prepared by | TandSol
Status | Living
Related documents | PD-CHR-001, PD-PMP-001, PD-RTM-001
Classification | Internal
Revision note | v1.0 — initial baseline issued with the first working build.

## Legend
Scoring key
| Score | Likelihood × Impact, computed by formula
| High | Score 15 or above — needs an owner and a dated action
| Medium | Score 8 to 14 — mitigate and monitor
| Low | Score 1 to 7 — accept and review at the next cycle
Likelihood
| 1 | Rare
| 2 | Unlikely
| 3 | Possible
| 4 | Likely
| 5 | Almost certain
Impact
| 1 | Negligible
| 2 | Minor
| 3 | Moderate
| 4 | Major
| 5 | Severe
Response
| Avoid | Remove the exposure
| Mitigate | Reduce likelihood or impact
| Transfer | Shift to another party
| Accept | Tolerate with monitoring

## Risk Register
Risk ID | Category | Description | Cause/Trigger | Impact | Likelihood (1-5) | Impact (1-5) | Score | Severity | Response | Mitigation | Owner | Status | Target Date
RSK-001 | Technical | Yahoo Finance chart endpoint starts requiring a crumb/cookie or blocks the client | Undocumented API hardening | Quotes, indices and hype radar go blank | 4 | 5 |  |  | Mitigate | Stooq CSV fallback is wired for US tickers; TTL cache serves the last good value; add a second provider (Twelve Data free tier) if failures persist | Owner | Open | 2026-09-15
RSK-002 | Technical | Binance API is geo-blocked or rate-limits the rolling-window endpoint | Regional restrictions or weight overrun | Crypto pump table degrades to a 1-hour CoinGecko proxy | 3 | 3 |  |  | Mitigate | CoinGecko fallback already implemented and labelled in the UI; request chunking keeps weight under the per-minute cap | Owner | Open | 2026-09-15
RSK-003 | Technical | An RSS publisher changes feed URL or format | Publisher CMS migration | One of eight sources drops out of the wire | 4 | 2 |  |  | Accept | Per-feed failures are isolated by the pool; the wire still renders from the remaining sources | Owner | Open | 2026-10-01
RSK-004 | Product | Users read the RISE/FALL badge as a price prediction | Label ambiguity | Misinformed trades, reputational harm | 3 | 5 |  |  | Mitigate | Handbook and in-app footer state it is headline tone, not a forecast; confidence bar shown alongside; no buy/sell language used | Owner | Open | 2026-09-01
RSK-005 | Technical | Sentiment lexicon misclassifies sarcasm, negation chains or non-English headlines | Rule-based classifier limits | Wrong direction call on individual items | 4 | 3 |  |  | Mitigate | Negation window and hedge damping implemented; confidence surfaces uncertainty; review lexicon quarterly against sampled headlines | Owner | Open | 2026-11-01
RSK-006 | Data | Corporate actions (splits, bonuses) distort average buy price and P&L | No corporate-action feed | Overstated or understated returns on affected holdings | 3 | 4 |  |  | Mitigate | Holdings are user-editable so the average price can be corrected; a corporate-action strip is on the roadmap | Owner | Open | 2026-12-01
RSK-007 | Data | FX cross unavailable, leaving foreign holdings valued at a 1:1 rate | Yahoo FX symbol failure | Materially wrong net worth | 2 | 5 |  |  | Mitigate | fxRate falls back to 1 and the failure is listed in the status bar; cache the last known cross across restarts (planned) | Owner | Open | 2026-09-30
RSK-008 | Security | Malicious content in a headline attempts script injection into the renderer | Untrusted third-party text | Renderer compromise | 2 | 5 |  |  | Mitigate | All remote text is HTML-escaped, CSP blocks inline and remote scripts, node integration is off | Owner | Closed | 2026-08-01
RSK-009 | Privacy | IP geolocation lookup discloses approximate user location to a third party | Weather needs coordinates | Privacy expectation mismatch | 3 | 2 |  |  | Mitigate | Manual latitude/longitude override in settings bypasses the lookup entirely; documented in the retention policy | Owner | Open | 2026-09-15
RSK-010 | Operational | Always-on-top window obscures other applications during screen sharing | Pinning is the default | User annoyance, accidental data exposure on shared screens | 4 | 2 |  |  | Mitigate | Ctrl+Alt+P hides instantly, tray toggles pinning, opacity and click-through modes available | Owner | Closed | 2026-08-01
RSK-011 | Technical | Electron major-version upgrade breaks transparency or always-on-top behaviour on Windows | Upstream Chromium changes | Widget stops behaving like a widget | 2 | 3 |  |  | Mitigate | Version pinned in package.json; smoke-test pinning and transparency before any upgrade | Owner | Open | 2027-01-15
RSK-012 | Operational | Single maintainer — no cover for defect response | Solo project | Slow fixes if the maintainer is unavailable | 3 | 3 |  |  | Accept | Codebase kept dependency-light and documented so a second developer can pick it up from the Code Register | Owner | Open | 2026-12-01

## Summary
Metric | Value
Total risks
High severity
Medium severity
Low severity
Open
Closed
Average score
Highest score