## Cover
PulseDesk — Requirements Traceability Matrix
Document ID | PD-RTM-001
Version | 1.0
Date | 2026-08-01
Prepared by | TandSol
Status | Baselined
Related documents | PD-CHR-001, PD-SDD-001, PD-CR-001, PD-PMP-001
Classification | Internal
Revision note | v1.0 — initial baseline issued with the first working build.

## Legend
Priority (MoSCoW)
| M | Must have — the build is not acceptable without it
| S | Should have — important but not fatal at release
| C | Could have — included when effort allows
| W | Won't have this release
Type
| FUN | Functional
| SEC | Security
| CMP | Compliance
| NFR | Non-functional
| INT | Integration
| RPT | Reporting
Status
| Proposed | Raised, not yet agreed
| Approved | Agreed for the release
| In Design | Being designed in the SDD
| Developed | Code written
| Tested | Exercised against live data
| Verified | Confirmed working in the running app
Conventions
| Design Ref | Section of PD-SDD-001 that realises the requirement
| Deprecated rows | Kept in place with a [DEPRECATED — reason] prefix, never deleted

## Functional RTM
Req ID | Module | Description | User Role | Pri | Type | Source | Design Ref | Test Ref | Compliance Tag | Status
FUN-001 | Hype Radar | Show the 5 most-hyped stocks with price, day change and sparkline | Investor | M | FUN | Charter §3.1 | SDD §4.2 | TC-F-001 | — | Verified
FUN-002 | Hype Radar | Rank hype as 0.45×volume-ratio + 0.35×¦move¦ + 0.20×news mentions, min-max normalised | Investor | M | FUN | Charter §3.1 | SDD §4.2 | TC-F-002 | — | Verified
FUN-003 | Hype Radar | Build the candidate universe from Yahoo trending, curated IN/US liquid names, holdings and headline tickers | System | S | FUN | Charter §3.1 | SDD §4.2 | TC-F-003 | — | Verified
FUN-004 | Portfolio | Add, merge (weighted average), edit and remove holdings | Investor | M | FUN | Charter §3.2 | SDD §4.5 | TC-F-004 | — | Verified
FUN-005 | Portfolio | Compute invested, current value, unrealised P&L and P&L% per holding and in total | Investor | M | FUN | Charter §3.2 | SDD §4.5 | TC-F-005 | — | Verified
FUN-006 | Portfolio | Compute day P&L from previous close and show it against net worth | Investor | M | FUN | Charter §3.2 | SDD §4.5 | TC-F-006 | — | Verified
FUN-007 | Portfolio | Book realised P&L into a trade log when a holding is closed with a sell price | Investor | S | FUN | Charter §3.2 | SDD §4.5 | TC-F-007 | — | Developed
FUN-008 | Portfolio | Convert every holding to a user-selected base currency using the live FX cross | Investor | M | FUN | Charter §3.2 | SDD §4.5 | TC-F-008 | — | Verified
FUN-009 | Portfolio | Show allocation weights as a donut with a legend of the top 8 positions | Investor | S | FUN | Charter §3.2 | SDD §5.3 | TC-F-009 | — | Verified
FUN-010 | Portfolio | Persist a daily net-worth snapshot and plot the trend | Investor | C | FUN | Charter §3.2 | SDD §4.5 | TC-F-010 | — | Verified
FUN-011 | Portfolio | Track idle cash separately and include it in net worth | Investor | C | FUN | Charter §3.2 | SDD §4.5 | TC-F-011 | — | Verified
FUN-012 | News Wire | Aggregate 8 RSS sources, de-duplicate by normalised headline and show the top 15 | Investor | M | FUN | Charter §3.3 | SDD §4.3 | TC-F-012 | — | Verified
FUN-013 | News Wire | Classify each headline as RISE / FALL / FLAT with a confidence percentage | Investor | M | FUN | Charter §3.3 | SDD §4.4 | TC-F-013 | — | Verified
FUN-014 | News Wire | Extract mentioned tickers from headlines and feed the counts into the hype scorer | System | S | FUN | Charter §3.3 | SDD §4.3 | TC-F-014 | — | Verified
FUN-015 | News Wire | Filter the wire by direction (All / Rise / Fall) | Investor | S | FUN | Charter §3.3 | SDD §5.3 | TC-F-015 | — | Verified
FUN-016 | News Wire | Open a headline in the system browser, never inside the app window | Investor | M | FUN | Charter §3.3 | SDD §6.3 | TC-S-004 | — | Verified
FUN-017 | Crypto | Rank the 10 strongest USDT pairs over an exact trailing 5-hour window | Crypto watcher | M | FUN | Charter §3.4 | SDD §4.6 | TC-F-017 | — | Verified
FUN-018 | Crypto | Exclude leveraged tokens, stablecoin pairs and pairs under $3M of 24h quote volume | System | S | FUN | Charter §3.4 | SDD §4.6 | TC-F-018 | — | Verified
FUN-019 | Crypto | Show Fear & Greed, total market cap, BTC dominance and 24h cap change | Crypto watcher | S | FUN | Charter §3.4 | SDD §4.6 | TC-F-019 | — | Verified
FUN-020 | Markets | Scroll a live tape of Indian and US indices, commodities, USD/INR and BTC | Investor | M | FUN | Charter §3.5 | SDD §4.1 | TC-F-020 | — | Verified
FUN-021 | Markets | Show open/closed state and countdown for NSE, NYSE, LSE, TSE and crypto | Desk operator | S | FUN | Charter §3.5 | SDD §4.7 | TC-F-021 | — | Verified
FUN-022 | Markets | Derive advance/decline breadth and a −100…+100 pulse mood score | Investor | S | FUN | Charter §3.5 | SDD §4.7 | TC-F-022 | — | Verified
FUN-023 | Weather | Show current temperature, feels-like, humidity, wind, rain chance, UV, AQI and 8 hourly steps | Investor | M | FUN | Charter §3.6 | SDD §4.8 | TC-F-023 | — | Verified
FUN-024 | Weather | Resolve location by IP with a manual latitude/longitude override | Investor | S | FUN | Charter §3.6 | SDD §4.8 | TC-F-024 | — | Verified
FUN-025 | Shell | Keep the window above other applications and optionally on every virtual desktop | Investor | M | FUN | Charter §3.7 | SDD §3.2 | TC-F-025 | — | Verified
FUN-026 | Shell | Offer tray control for show/hide, pinning, opacity, click-through and data folder | Investor | M | FUN | Charter §3.7 | SDD §3.3 | TC-F-026 | — | Verified
FUN-027 | Shell | Register Ctrl+Alt+P (toggle) and Ctrl+Alt+R (refresh) global shortcuts | Investor | S | FUN | Charter §3.7 | SDD §3.3 | TC-F-027 | — | Verified
FUN-028 | Shell | Refresh on tiers — 60 s market, 5 min news/hype, 30 min weather | System | M | FUN | Charter §3.7 | SDD §3.4 | TC-F-028 | — | Verified
FUN-029 | Shell | Persist window bounds, pinning, opacity and compact mode between sessions | Investor | S | FUN | Charter §3.7 | SDD §3.6 | TC-F-029 | — | Verified
FUN-030 | Shell | Validate a symbol against the live quote service before a holding is saved | Investor | C | FUN | Charter §3.2 | SDD §4.5 | TC-F-030 | — | Verified
FUN-031 | Shell | Offer a two-column compact layout for narrow placements | Investor | C | FUN | Charter §3.7 | SDD §5.2 | TC-F-031 | — | Verified
FUN-032 | Distribution | Serve the same dashboard as an installable web app on Android, iOS and desktop browsers | Public user | M | FUN | Charter §3.8 | SDD §10.2 | TC-F-032 | — | Verified
FUN-033 | Distribution | Cache the app shell in a service worker so it opens without a connection | Public user | S | FUN | Charter §3.8 | SDD §10.3 | TC-F-033 | — | Developed
FUN-034 | Distribution | Route web market data through an edge worker because browsers cannot call the upstreams directly | System | M | FUN | Charter §3.8 | SDD §10.1 | TC-F-034 | — | Verified
FUN-035 | Distribution | Keep web holdings in browser local storage so the web build needs no account either | Public user | M | FUN | Charter §3.8 | SDD §10.2 | TC-F-035 | — | Verified
FUN-036 | Analytics | Count app opens, distinct devices per day and devices active in the last five minutes without any login | Owner | M | FUN | Charter §3.9 | SDD §11.1 | TC-F-036 | DPDP §4 | Developed
FUN-037 | Analytics | Present those counts on a private dashboard gated by a shared key, with a 30-day trend, country and platform split | Owner | S | FUN | Charter §3.9 | SDD §11.2 | TC-F-037 | — | Developed
FUN-038 | Distribution | Publish the Windows installer and portable build automatically from a version tag | Owner | S | FUN | Charter §3.8 | SDD §10.4 | TC-F-038 | — | Developed
FUN-039 | Distribution | Show a subtle author credit in the status bar, title bar, tray menu, manifest and packaged metadata | Owner | S | FUN | Charter §3.10 | SDD §5.1 | TC-F-039 | — | Verified
FUN-040 | Portfolio | Offer a type-ahead list of matching companies and tickers as the user types a name | Investor | M | FUN | Charter §3.2 | SDD §4.9 | TC-F-040 | — | Verified
FUN-041 | Portfolio | Let the user say the purchase was "right now" or pick an exact past date and time | Investor | M | FUN | Charter §3.2 | SDD §4.10 | TC-F-041 | — | Verified
FUN-042 | Portfolio | Fill the buy price automatically from the market price at the chosen moment, widening to the nearest trading time when markets were shut | Investor | M | FUN | Charter §3.2 | SDD §4.10 | TC-F-042 | — | Verified
FUN-043 | Portfolio | Preview invested amount and the gain or loss against the live price before the holding is saved | Investor | S | FUN | Charter §3.2 | SDD §4.10 | TC-F-043 | — | Verified
FUN-044 | Portfolio | Allow the auto-filled price to be overridden and label it as the user’s own figure | Investor | S | FUN | Charter §3.2 | SDD §4.10 | TC-F-044 | — | Verified
FUN-045 | Portfolio | Record the purchase timestamp and show holding age and since-date on each row | Investor | S | FUN | Charter §3.2 | SDD §4.5 | TC-F-045 | — | Verified
FUN-046 | Portfolio | Offer a one-click INR/USD switch beside the full base-currency list | Investor | M | FUN | Charter §3.2 | SDD §5.3 | TC-F-046 | — | Verified
FUN-047 | Portfolio | Place the portfolio first on the dashboard, across the full width | Investor | M | FUN | Charter §3.2 | SDD §5.2 | TC-F-047 | — | Verified
FUN-048 | Popular | List widely-held large caps ranked by 1-year annualised volatility, with a plain-English steadiness band and 1-year return | Investor | M | FUN | Charter §3.11 | SDD §4.11 | TC-F-048 | — | Verified
FUN-049 | Popular | Filter that list by India or US and add any row straight into the portfolio | Investor | S | FUN | Charter §3.11 | SDD §4.11 | TC-F-049 | — | Verified
FUN-050 | Crypto | Offer a most-bought view ranked by 24-hour turnover alongside the 5-hour pump view | Crypto watcher | M | FUN | Charter §3.4 | SDD §4.6 | TC-F-050 | — | Verified
FUN-051 | Shell | Provide a full-screen control in the title bar and on F11 | Investor | M | FUN | Charter §3.7 | SDD §3.2 | TC-F-051 | — | Verified
FUN-052 | Distribution | Ship the worker as one pasteable file so publishing needs no command line | Owner | M | FUN | Charter §3.12 | SDD §10.6 | TC-F-052 | — | Verified
FUN-053 | Distribution | Provide double-click launchers and a click-by-click publishing guide for a non-technical operator | Owner | M | FUN | Charter §3.12 | SDD §10.6 | TC-F-053 | — | Verified

## Security RTM
Req ID | Module | Description | User Role | Pri | Type | Source | Design Ref | Test Ref | Compliance Tag | Status
SEC-001 | Shell | Renderer runs with contextIsolation on and nodeIntegration off | System | M | SEC | OWASP Electron | SDD §6.1 | TC-S-001 | CERT-In | Verified
SEC-002 | Shell | Renderer enforces a CSP of default-src self; script-src self | System | M | SEC | OWASP Electron | SDD §6.1 | TC-S-002 | CERT-In | Verified
SEC-003 | Renderer | Every remote string is HTML-escaped before insertion into the DOM | System | M | SEC | OWASP A03 | SDD §6.2 | TC-S-003 | CERT-In | Verified
SEC-004 | Shell | window.open is denied; links open through shell.openExternal only | System | M | SEC | OWASP Electron | SDD §6.3 | TC-S-004 | CERT-In | Verified
SEC-005 | Shell | shell:open accepts http/https URLs only | System | M | SEC | OWASP A01 | SDD §6.3 | TC-S-005 | CERT-In | Verified
SEC-006 | Services | No API keys, tokens or credentials exist in the repository or runtime | System | M | SEC | OWASP A07 | SDD §6.4 | TC-S-006 | DPDP §8 | Verified
SEC-007 | Storage | Portfolio and settings are stored locally; nothing is uploaded to any server | Investor | M | SEC | DPDP Act 2023 | SDD §6.5 | TC-S-007 | DPDP §4, §8 | Verified
SEC-008 | Services | Outbound calls are limited to the documented public endpoints; no user data is sent as a parameter | System | M | SEC | DPDP Act 2023 | SDD §6.5 | TC-S-008 | DPDP §8 | Verified
SEC-009 | Services | All network calls carry an abort timeout so a hostile or hung endpoint cannot stall the app | System | S | SEC | CERT-In | SDD §3.7 | TC-S-009 | CERT-In | Verified
SEC-010 | Renderer | Preview server binds to localhost and refuses paths outside the renderer directory | Developer | C | SEC | OWASP A01 | SDD §7.2 | TC-S-010 | — | Verified
SEC-011 | Analytics | The statistics endpoint is refused without the shared key held as a worker secret | Owner | M | SEC | OWASP A01 | SDD §11.2 | TC-S-011 | — | Developed
SEC-012 | Analytics | No IP address, cookie, email or account is stored — only a random client-generated id, coarse country and platform | Public user | M | SEC | DPDP Act 2023 | SDD §11.1 | TC-S-012 | DPDP §4, §8 | Developed
SEC-013 | Worker | The worker holds no upstream credentials and accepts only its documented routes | System | M | SEC | OWASP A05 | SDD §10.1 | TC-S-013 | CERT-In | Developed
SEC-014 | Worker | Visitor identifiers are sanitised and length-capped before they reach the database | System | S | SEC | OWASP A03 | SDD §11.1 | TC-S-014 | — | Developed
SEC-015 | Distribution | The web build declares a content security policy that allows connections only to its own origin and the configured worker | Public user | M | SEC | OWASP A05 | SDD §10.2 | TC-S-015 | — | Verified

## NFR RTM
Req ID | Module | Description | User Role | Pri | Type | Source | Design Ref | Test Ref | Compliance Tag | Status
NFR-001 | Shell | Cold start to first paint under 3 seconds on a mid-range Windows laptop | Investor | M | NFR | Charter §4 | SDD §3.1 | TC-N-001 | — | Verified
NFR-002 | Services | Market data no older than 60 seconds while the app is visible | Investor | M | NFR | Charter §4 | SDD §3.4 | TC-N-002 | — | Verified
NFR-003 | Services | A failing feed never blanks the dashboard — the last good value is served and the error is surfaced in the status bar | Investor | M | NFR | Charter §4 | SDD §3.7 | TC-N-003 | — | Verified
NFR-004 | Services | Outbound requests are pooled at a maximum of 8 concurrent calls to stay inside free rate limits | System | M | NFR | Charter §4 | SDD §3.7 | TC-N-004 | — | Verified
NFR-005 | Project | Zero paid services, subscriptions or API keys | Owner | M | NFR | Charter §2 | SDD §2.2 | TC-N-005 | — | Verified
NFR-006 | Renderer | Layout stays legible from 1240 px down to 620 px with no horizontal scrolling | Investor | S | NFR | Charter §4 | SDD §5.2 | TC-N-006 | GIGW 3.0 | Verified
NFR-007 | Renderer | Colour is never the only signal — direction is also carried by arrow glyphs and text | Investor | S | NFR | WCAG 2.1 AA | SDD §5.4 | TC-N-007 | GIGW 3.0 | Verified
NFR-008 | Shell | Closing the window leaves the app resident in the tray rather than quitting | Investor | S | NFR | Charter §4 | SDD §3.3 | TC-N-008 | — | Verified
NFR-009 | Project | No build step for the renderer — plain HTML/CSS/JS so the app stays auditable | Owner | C | NFR | Charter §4 | SDD §2.2 | TC-N-009 | — | Verified
NFR-010 | Services | Every primary data source has a documented fallback path | System | S | NFR | Charter §4 | SDD §2.3 | TC-N-010 | — | Verified
NFR-011 | Worker | Edge caching holds worker traffic inside the free allowance at ten thousand daily users | Owner | M | NFR | Charter §2 | SDD §10.1 | TC-N-011 | — | Developed
NFR-012 | Distribution | The phone layout fits a 375 px viewport with no horizontal scrolling and safe-area padding | Public user | M | NFR | Charter §3.8 | SDD §10.2 | TC-N-012 | GIGW 3.0 | Verified
NFR-013 | Distribution | Hosting, delivery and analytics stay at zero recurring cost | Owner | M | NFR | Charter §2 | SDD §10.5 | TC-N-013 | — | Verified

## Role Ref
Role | Description
Investor | Primary user tracking a personal portfolio and the market tape
Crypto watcher | User focused on short-horizon crypto momentum
Desk operator | User who needs session state and clocks at a glance
Developer | Maintainer working on the codebase
Owner | TandSol — accountable for scope, risk and releases
System | Behaviour with no direct user interaction

## Summary
Metric | Value
Functional requirements
Security requirements
NFR requirements
Total requirements
Must-have count
Verified
Developed (not yet verified)
Percent verified